## User Story
AGILE USER STORY
Feature ID | Feature Name | User Stroy ID | Priority | As a <type of user> | I want to<perform some task> | So that I can<achive some goals>
F1 | User | 1.1 | High | User | Register | Create an User to Login
|  | 1.2 | High | User | Login | Login to the system
|  | 1.3 | Low | User | View Profile | Update my profile
F2 | Dashboard | 2.1 | High | User | Choose Categories | Choose which type of items he/she want to order
|  | 2.2 | High | User | Choose Membership | Select the mombership
|  | 2.3 | High | User | View Notification | Check their informations
|  | 2.4 | High | User | Track Gym clup in maps | Choose the nearest Gym clubs
F3 | Giftcard Packages | 3.1 | High | Admin | Add various packages | view, update and delete the packages as necessity.
|  | 3.2 | High | Admin | Add various schemas | users can enjoy the various schemas
|  | 3.3 | Medium | Admin | Add Packages details | update package details and validity
|  | 3.4 | Medium | User | Choose relevant packages | Choose different packages
F4 | Services | 4.1 | High | User | inquiry of packages | Get information of the packages
|  | 4.2 | Low | Staff | Check user Details | View registered user details
|  | 4.3 | Low | Staff | Service Confirmation | Confirm the user purchases
|  | 4.5 | Medium | User | Cancel purchase order | Member's can eaisly cancl the booking
|  | 4.6 | Medium | User | Booking of Services | entertain the service quality
|  | 4.7 | High | User | Redeem Membership | easily expand membership validation
|  |  | Medium | User | Reffer | Recommend similar services to others
|  | 4.8 | High | User | Online Payment | pay digitially with eSewa and fonePay
F5 | Feedback & Rating | 5.1 | Low | User | Rate the wellness hub | Give feedback and rate the wellness on the basis of the services and packages

## User Story MapBoard
the BACKBONE | Epic 1 | Epic 2 | Epic 3 | Epic 4 | Epic 5
FLESH on the backbone | User | Dashboard | Items | Service | Feedback &Rating
Sprint / Iteration 1 | US01: Register
(07/19/2021-07/20/2021)
SEQUENCE
Version 1.0 | US02: Login
US03: View Profile
Sprint / Iteration 2 |  | US04: Choose Categories
(07/26/2021-07/30/2021)
US05: Choose Membership
Version 2.0 |  | US06: View Notification
US07: Track Gym clup in maps
Sprint / Iteration 3 |  |  | US08: Add various packages
(08/02/2021-08/06/2021)
Version 3.0 |  |  | US9: Add various schemas
US10 : Add Packages details
US11: Choose relevant packages
Sprint / Iteration 4 |  |  |  | US12: Inquiry of packages
(08/09/2021-08/13/2021)
Version 4.0 |  |  |  | US13: Check user Details
US14: Service Confirmation
US15: Cancel purchase order
US16: Booking of Services
US17: Redeem Membership
US18: Reffer
US19: Online Payment
Sprint / Iteration 5
(08/16/2021-08/20/2021) | [5 empty] | US20: Rate the wellness hub
Version 5.0

## Product Backlog
Product Backlog
Feature ID | Feature Name | User Stroy ID | Priority | As a <type of user> | I want to<perform some task> | So that I can<achive some goals>
F1 | User | 1.1 | HIGH | User | Sign Up | Create an User to Login
|  | 1.2 | HIGH | User | Login | Login to the system
|  | 1.3 | LOW | User | View Profile | Update my profile
F2 | Dashboard | 2.1 | HIGH | User | Choose Category | So that user can choose which type of items he/she want to order
|  | 2.2 | HIGH | User | Choose Mebership | So users select their memberships
|  | 2.3 | HIGH | User | View notification | So that user can cheack their abability
|  | 2.4 | HIGH | User | Track Gym club in maps | Choose the nearest Gym clubs
F3 | Packages | 3.1 | HIGH | Admin | Add various Packages | So the useser can choose their different packages
|  | 3.2 | HIGH | Admin | Add various schemes | User's can enjoy various services
|  | 3.3 | MEDIUM | Admin | Add Packages details | Upload package details and validity
|  | 3.4 | MEDIUM | User | Choose relevant Packages | Can choose different Packages
F4 | Services | 4.1 | HIGH | User | Enquery of Packages | Get information of the packages
|  | 4.2 | LOW | Staff | Check user Details | View user's Mebership details
|  | 4.3 | LOW | Staff | Service Conformation | Confirm the user application
|  | 4.4 | MEDIUM | User | Booking of services | To entertainment the services
|  | 4.5 | MEDIUM | User | Cancel booking | Member's can eaisly cancle the booking
|  | 4.6 | HIGH | user | Renew Membership | Can eaissly expand membership validitaion
|  | 4.7 | LOW | User | Reffer | recommend similar services to others
|  | 4.8 | HIGH | User | Payment | easily make payments for services and memberships
F5 | Feedback & Rating | 5.1 | LOW | User | Rate the welnnes hub | Give feedback and rate the wellness on the basis of the service and Packages

## Agile Release Plan
RELEASE PLAN
AT RISK | SPRINT | USER STORY NAME | STORY POINTS | FEATURE TYPE | START | FINISH | DURATION (In hours) | STATUS | RELEASE DATE
| 1 | Sign Up | 1 | Functionality | 2021-07-19 | 2021-07-20 | 6 | Planned | 2021-07-23
| 1 | Login | 1 | Functionality | 2021-07-20 | 2021-07-21 | 6 | Planned | 2021-07-23
| 1 | View Profile | 1 | Functionality | 2021-07-21 | 2021-07-22 | 6 | Planned | 2021-07-23
| 1 | Choose Category | 2 | Functionality | 2021-07-22 | 2021-07-23 | 12 | Planned | 2021-07-23
| 2 | View Notifaction | 1 | Functionality | 2021-07-26 | 2021-07-27 | 6 | Planned | 2021-07-30
| 2 | Choose Category | 2 | Functionalitiy | 2021-07-27 | 2021-07-28 | 12 | Planned | 2021-07-30
| 2 | Choose Mebership | 1 | Functionalitiy | 2021-07-28 | 2021-07-29 | 6 | Planned | 2021-07-30
| 2 | Track Gym club in maps | 1 | Functionality | 2021-07-29 | 2021-07-30 | 6 | Planned | 2021-07-30
| 3 | Add various Packages | 2 | Functionality | 2021-08-02 | 2021-08-03 | 12 | Planned | 2021-08-06
| 3 | Add various schemes | 1 | Functionallity | 2021-08-03 | 2021-08-04 | 6 | Planned | 2021-08-06
| 3 | Add Packages details | 1 | Functionallity | 2021-08-04 | 2021-08-05 | 6 | Planned | 2021-08-06
| 3 | Choose relevant Packages | 1 | Functionallity | 2021-08-05 | 2021-08-06 | 6 | Planned | 2021-08-06
| 4 | Enquery of Packages | 1 | Functionallity | 2021-08-09 | 2021-08-10 | 6 | Planned | 2021-08-13
| 4 | Check user Details | 1 | Functionallity | 2021-08-10 | 2021-08-11 | 6 | Planned | 2021-08-13
| 4 | Booking of services | 1 | Functionallity | 2021-08-11 | 2021-08-12 | 6 | Planned | 2021-08-13
| 4 | Renew Membership | 2 | Functionallity | 2021-08-12 | 2021-08-13 | 12 | Planned | 2021-08-13
| 5 | Payment | 2 | Functionallity | 2021-08-16 | 2021-08-17 | 12 | Planned | 2021-08-20
| 5 | Cancel booking | 1 | Functionallity | 2021-08-17 | 2021-08-18 | 6 | Planned | 2021-08-20
| 5 | Reffer | 1 | Functionallity | 2021-08-18 | 2021-08-19 | 6 | Planned | 2021-08-20
| 5 | Feedback and rating | 1 | Functionallity | 2021-08-19 | 2021-08-20 | 6 | Planned | 2021-08-20
Total |  |  | 25 |  |  |  | 150

## Sprint BackLog 1
Backlog Task & ID | Story Points | Assigned To | Status | Original Estimate (In hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US01: Register | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US02: Login | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 2
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 1
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US03: View Profile | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
Total | 5 |  |  | 30

## Sprint BackLog 2
Backlog Task & ID | Story Points | Assigned To | Status | Original Estimate (In hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US04: Choose Categories | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US05: Choose Membership | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 2
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 1
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US06: View Notification | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US07: Track Gym clup in maps | 2 |  |  | 12
Backend development |  | Aavash Neupane |  | 4
Frontend Development |  | Ritesh Raj Maharjan |  | 2
Development (Integration API and Frontend) |  | Raj Shrestha |  | 4
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
Total | 5 |  |  | 30

## Sprint BackLog 3
Backlog Task & ID | Story Points | Assigned To | Status | Original Estimate (In hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US08: Add various packages | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US9: Add various schemas | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 2
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 1
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US10 : Add Packages details | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US11: Choose relevant packages | 2 |  |  | 12
Backend development |  | Aavash Neupane |  | 4
Frontend Development |  | Ritesh Raj Maharjan |  | 2
Development (Integration API and Frontend) |  | Raj Shrestha |  | 4
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
Total | 5 |  |  | 30

## Sprint BackLog 4
Backlog Task & ID | Story Points | Assigned To | Status | Original Estimate (In hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US12: Inquiry of packages | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US13: Check user Details | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 2
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 1
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US14: Service Confirmation | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US15: Cancel purchase order | 2 |  |  | 12
Backend development |  | Aavash Neupane |  | 4
Frontend Development |  | Ritesh Raj Maharjan |  | 2
Development (Integration API and Frontend) |  | Raj Shrestha |  | 4
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US16: Booking of Services | 1 |  |  | 8
Backend development |  | Aavash Neupane |  | 2
Frontend Development |  | Ritesh Raj Maharjan |  | 2
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US17: Redeem Membership | 1 |  |  | 10
Backend development |  | Aavash Neupane |  | 3
Frontend Development |  | Ritesh Raj Maharjan |  | 2
Development (Integration API and Frontend) |  | Raj Shrestha |  | 3
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US18: Reffer | 1 |  |  | 8
Backend development |  | Aavash Neupane |  | 2
Frontend Development |  | Ritesh Raj Maharjan |  | 2
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
US19: Online Payment | 1 |  |  | 13
Backend development |  | Aavash Neupane |  | 4
Frontend Development |  | Ritesh Raj Maharjan |  | 3
Development (Integration API and Frontend) |  | Raj Shrestha |  | 4
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
Total | 5 |  |  | 30

## Sprint BackLog 5
Backlog Task & ID | Story Points | Assigned To | Status | Original Estimate (In hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US20: Rate the wellness hub | 1 |  |  | 6
Backend development |  | Aavash Neupane |  | 1
Frontend Development |  | Ritesh Raj Maharjan |  | 1
Development (Integration API and Frontend) |  | Raj Shrestha |  | 2
TDD Testing |  | Kushal Shrestha |  | 1
BDD Testing |  | Aayush Maharjan |  | 1
Total | 5 |  |  | 30